## Worksheet Template A
LEA Goals and Grant Source Management Timeline Worksheet
| LEA NAME: |  |  |  |  | Team Members: |  |  |  |  | Date: |  | Update: |  |  |  |  | Guidance:
I | Write a goal that aligns with identified needs of the LEA and Students with Disabilities. Establish at least | [16 empty] | Section I is designed for the District
one Objective (others can be added later) to ensure the team is headed toward the attainable Goal. | [17 empty] | Team to develop sustainable supports
| Goal (G): | [16 empty] | through small steps (objectives) aligned
| Objective #1: | [16 empty] | to LEA initiatives for accomplishable
| Objective #2: | [16 empty] | goals with braided grant sources.
| Objective #3: | [16 empty] | Use as many pages as needed (or PDF).
II | Place symbol G1 (Goal) and Objectives (O1) above the month that the team projects actions to occur. | [16 empty] | Section II is a managerial time
Place an arrow or color bar along the funding source - projected balances should be updated regularly. | [17 empty] | grid that follows the FY22 year.
| Start | [12 empty] | Tip: Work backwards |  |  |  | Place in the Goal (G) and small
Source | 7.21 | 8.21 | 9.21 | 10.21 | 11.21 | 12.21 | 1.22 | 2.22 | 3.22 | 4.22 | 5.22 | 6.22 |  | from end date to present. |  |  |  | steps (Objectives).
Local | [13 empty] | Tip: Have standing
State | [13 empty] | goal/source review |  |  |  | Determine funding source from
a. | [13 empty] | meetings with team |  |  |  | list codes below and place in
b. | [13 empty] | on a regular basis. |  |  |  | arrows/color bar along
c. | [13 empty] | Tip: Consider running |  |  |  | the time line.
d. | [13 empty] | grant source scenarios
e. | [13 empty] | in LEA MOE Calculator |  |  |  | Place in projected running
f. | [13 empty] | throughout year. |  |  |  | balances in order to know status.
[12 empty] | End | obligate |  | liquidate | Grant Sources Codes/ Definitions List
Source | 7.22 | 8.22 | 9.22 | 10.22 | 11.22 | 12.22 | 1.23 | 2.23 | 3.23 | 4.23 | 5.23 | 6.23 | 7.23 | 8.23 | 9.23 | with approximate funding/balance amount.
Local | [15 empty] | Local | Local Special Education Fund $
State | [15 empty] | State | ECS/ExcessCost Grant $
a. | [15 empty] | a. | IDEA Part B $
b. | [15 empty] | b. | ARP IDEA Part B $
c. | [15 empty] | c.
d. | [15 empty] | d.
e. | [15 empty] | e.
f. | [15 empty] | f.

## Example #1 no balances
LEA Goals and Grant Source Management Timeline Worksheet
| LEA NAME: |  | Happy Town |  |  | Team Members: |  | TB, AB, AT, MT |  |  | Date: | 11.1.21 | Update: |  |  |  |  | Guidance:
I | Write a goal that aligns with identified needs of the LEA and Students with Disabilities. Establish at least | [16 empty] | Section I is designed for the District
one Objective (others can be added later) to ensure the team is headed toward the attainable Goal. | [17 empty] | Team to develop sustainable supports
| Goal (G): |  | Establish the use of Read and Writing Apps across the District. | [14 empty] | through small steps (objectives) aligned
| Objective #1: |  | Contact RESC/NEAT/SERC schedule consult and training | [14 empty] | to LEA initiatives for accomplishable
| Objective #2: |  | Get License for Read and Write | [14 empty] | goals with braided grant sources.
| Objective #3: |  | Impliment with CEIS (non-disabled) - struggling readers with IEPs | [14 empty] | Use as many pages as needed.
II | Place symbol G (Goal) and Objectives (O1) above the month that the team projects actions to occur. | [16 empty] | Section II is a managerial time
Place an arrow or color bar along the funding source - projected costs/balances should be updated regularly. | [17 empty] | grid that follows the FY22 year.
| start |  |  |  | 1 | 2 |  | 3 | [6 empty] | Tip: Work backwards |  |  | Place in the Goal (G) and small
Source | 7.21 | 8.21 | 9.21 | 10.21 | 11.21 | 12.21 | 1.22 | 2.22 | 3.22 | 4.22 | 5.22 | 6.22 |  |  | from end date to present. |  |  | steps (Objectives).
Local |  |  |  |  | pay for APP license 25k for all students with disabilities in LEA through 6/30/23 | [9 empty] | Tip: Have standing
State | [14 empty] | goal/source review |  |  | Determine funding source from
a. | [5 empty] | NEAT Training of Special Ed Staff 3k, | [8 empty] | meetings with team |  |  | list codes below and place in
b. | [7 empty] | CEIS - stuggling readers nondisabled kids 1k | [6 empty] | on a regular basis. |  |  | arrows/color bar along
c. | [14 empty] | Tip: Consider running |  |  | the time line.
d. | [14 empty] | grant source scenarios
e. | [14 empty] | in LEA MOE Calculator |  |  | Place in projected running
f. | [14 empty] | throughout year. |  |  | balances in order to know status.
|  |  | G | [8 empty] | End | obligate |  | liquidate | Grant Sources Codes/ Definitions List with
Source | 7.22 | 8.22 | 9.22 | 10.22 | 11.22 | 12.22 | 1.23 | 2.23 | 3.23 | 4.23 | 5.23 | 6.23 | 7.23 | 8.23 | 9.23 | approximate cost funding/balance amount.
Local | NOTE: All School App is 50K only use 25K out of local Special Education budget. | [14 empty] | Local | Local Spec Ed Fund
State | [15 empty] | State | ECS/ExcessCost Grant
a. | IDEA Part B Salaries 17k | [14 empty] | a. | IDEA Part B
b. | [15 empty] | b. | ARP IDEA Part B
c. |  |  | ESSER II Dyslexia 5k | [12 empty] | c. | Esser II - Dyslexia
d. | [15 empty] | d.
e. | [15 empty] | e.
f. | [15 empty] | f.

## Example #1 with balances
LEA Goals and Grant Source Management Timeline Worksheet
| LEA NAME: |  | Happy Town |  |  | Team Members: |  | TB, AB, AT, MT |  |  | Date: | 11.1.21 | Update: |  |  |  |  | Guidance:
I | Write a goal that aligns with identified needs of the LEA and Students with Disabilities. Establish at least | [16 empty] | Section I is designed for the District
one Objective (others can be added later) to ensure the team is headed toward the attainable Goal. | [17 empty] | Team to develop sustainable supports
| Goal (G): |  | Establish the use of Read and Writing Apps across the District. | [14 empty] | through small steps (objectives) aligned
| Objective #1: |  | Contact RESC/NEAT/SERC schedule consult and training | [14 empty] | to LEA initiatives for accomplishable
| Objective #2: |  | Get License for Read and Write | [14 empty] | goals with braided grant sources.
| Objective #3: |  | Impliment with CEIS (non-disabled) - struggling readers with IEPs | [14 empty] | Use as many pages as needed.
II | Place symbol G (Goal) and Objectives (O1) above the month that the team projects actions to occur. | [16 empty] | Section II is a managerial time
Place an arrow or color bar along the funding source - projected costs/balances should be updated regularly. | [17 empty] | grid that follows the FY22 year.
| start |  |  |  | 1 | 2 |  | 3 | [6 empty] | Tip: Work backwards |  |  | Place in the Goal (G) and small
Source | 7.21 | 8.21 | 9.21 | 10.21 | 11.21 | 12.21 | 1.22 | 2.22 | 3.22 | 4.22 | 5.22 | 6.22 |  |  | from end date to present. |  |  | steps (Objectives).
Local |  |  |  |  | pay for APP license 25k for all students with disabilities in LEA through 6/30/23 | [9 empty] | Tip: Have standing
State | RESC to Assess Needs 10k | [13 empty] | goal/source review |  |  | Determine funding source from
a. | [5 empty] | NEAT Training of Special Ed Staff 3k, | [8 empty] | meetings with team |  |  | list codes below and place in
b. | [7 empty] | CEIS - stuggling readers nondisabled kids 1k | [6 empty] | on a regular basis. |  |  | arrows/color bar along
c. | [14 empty] | Tip: Consider running |  |  | the time line.
d. | [14 empty] | grant source scenarios
e. | [14 empty] | in LEA MOE Calculator |  |  | Place in projected running
f. | [14 empty] | throughout year. |  |  | balances in order to know status.
|  |  | G | [8 empty] | End | obligate |  | liquidate | Grant Sources Codes/ Definitions List with
Source | 7.22 | 8.22 | 9.22 | 10.22 | 11.22 | 12.22 | 1.23 | 2.23 | 3.23 | 4.23 | 5.23 | 6.23 | 7.23 | 8.23 | 9.23 | approximate cost funding/balance amount.
Local | NOTE: All School App is 50K only use 25K out of local Special Education budget due to 50% use will be by SWD. | [14 empty] | Local | Local Spec Ed Fund - 25k/150k
State | [15 empty] | State | ECS/ExcessCost Grant 10k/$ 100k
a. | IDEA Part B Salaries 17k | [14 empty] | a. | IDEA Part B 80k (611 - 20k/68K, 619 - 0k/12k)
b. | [15 empty] | b. | ARP IDEA Part B $10K (611 - CEIS 1k/7k, 619 - 0k/2k)
c. |  |  | ESSER II Dyslexia 5k / Contract with SERC | [12 empty] | c. | Esser II - Dyslexia (5k/5k)
d. | [15 empty] | d.
e. | [15 empty] | e.
f. | [15 empty] | f.

## Set A Example 3 later 2.22 w$
LEA Goals and Grant Source Management Timeline Worksheet
| LEA NAME: |  | Happy Town |  |  | Team Members: |  | TB, AB, AT, MT |  |  | Date: | 11.1.21 | Update: | 2.1.22 |  |  |  |  | Guidance:
I | Write a goal that aligns with identified needs of the LEA and Students with Disabilities. Establish | [17 empty] | Section I is designed for the District
Objective to ensure the team is headed toward the attainable Goal. | [18 empty] | Team to develop sustainable supports
| Goal (G): |  | Establish the use of Read and Writing Apps across the District. | [15 empty] | through small steps (objectives) aligned
| Objective #1: |  | Contact RESC/NEAT/SERC schedule consult and training | [15 empty] | to LEA initiatives for accomplishable
| Objective #2: |  | Get License for Read and Write | [5 empty] | (O2b. Udate apps as pilot in spring/across school in fall) | [9 empty] | goals with braided grant sources.
| Objective #3: |  | Impliment CEIS and struggling readers | [6 empty] | (O3b. Impliment with All IEPs with Dyslexia) | [8 empty] | Use as many pages as needed.
II | Place symbol G (Goal) and Objectives (#'s) above the month that the team projects actions to occur. | [17 empty] | Section II is a managerial time
Place an arrow or color bar along the funding source - projected costs/balances should be updated regularly. | [18 empty] | grid that follows the FY22 year.
| start |  |  |  | 2 |  | 3 | 1 & 2b | [6 empty] | Tip: Work backwards |  |  |  | Place in the Goal (G) and small
Source | 7.21 | 8.21 | 9.21 | 10.21 | 11.21 | 12.21 | 1.22 | 2.22 | 3.22 | 4.22 | 5.22 | 6.22 | Total |  | from end date to present. |  |  |  | steps (Objectives).
Local |  |  |  |  | pay for APP license 25k for all students with disabilities in LEA through 6/30/23 | [7 empty] | 13K |  | Tip: Have standing
State | RESC to Assess Needs 10k | [11 empty] | 0 |  | goal/source review |  |  |  | Determine funding source from
a. | [7 empty] | NEAT Training of Special Ed Staff 3k, |  |  |  |  | 3k |  | meetings with team |  |  |  | list codes below and place in
b. | [6 empty] | CEIS - stuggling readers nondisabled kids 1k | [5 empty] | 1k |  | on a regular basis. |  |  |  | arrows/color bar along
c. | [14 empty] | Tip: Consider running |  |  |  | the time line.
d. | [14 empty] | grant source scenarios
e. | [14 empty] | in LEA MOE Calculator |  |  |  | Place in projected running
f. | [14 empty] | throughout year. |  |  |  | balances in order to know status.
|  |  | 3a |  | 2b |  | 3a |  |  | G |  | End | obligate |  | liquidate |  | Grant Sources Codes/ Definitions List with
Source | 7.22 | 8.22 | 9.22 | 10.22 | 11.22 | 12.22 | 1.23 | 2.23 | 3.23 | 4.23 | 5.23 | 6.23 | 7.23 | 8.23 | 9.23 | Total | approximate cost funding/balance amount.
Local | NOTE: All School App is 50K only use 25K out of local Special Education budget. | [14 empty] | 12k | Local | Local Spec Ed Fund - 25k/150k
State | [16 empty] | State | ECS/ExcessCost Grant 10k/$ 100k
a. | IDEA Part B Salaries 17k | [14 empty] | 10k | a. | IDEA Part B 80k (611 - 20k/68K, 619 - 0k/12k)
b. | [6 empty] | Manage IEPs 6k | [8 empty] | 6k | b. | ARP IDEA Part B $10K (611 - CEIS 7k/7k, 619 - 0k/2k)
c. |  |  | ESSER II Dyslexia 5k | [12 empty] | 5k | c. | Esser II - Dyslexia (5k/5k)
d. | [16 empty] | d.
e. | [16 empty] | e.
f. | [16 empty] | f.

## Set A Ex. 4 Bonus & ESY$
LEA Goals and Grant Source Management Timeline Worksheet
| LEA NAME: |  | Happy Town |  |  | Team Members: |  | TB, AB, AT, MT |  |  | Date: | 11.1.21 | Update: | 2.1.22, 5.1.22 |  |  |  |  | Guidance:
I | Write a goal that aligns with identified needs of the LEA and Students with Disabilities. Establish at least | [17 empty] | Section I is designed for the District
one Objective (others can be added later) to ensure the team is headed toward the attainable Goal. | [18 empty] | Team to develop sustainable supports
| Goal (G): |  | Establish the use of Read and Writing Apps across the District. | [15 empty] | through small steps (objectives) aligned
| Objective #1: |  | Contact RESC/NEAT/SERC schedule consult and training | [15 empty] | to LEA initiatives for accomplishable
| Objective #2: |  | Get License for Read and Write | [5 empty] | (O2b. Udate apps as pilot in spring/across school in fall) | [9 empty] | goals with braided grant sources.
| Objective #3: |  | Impliment CEIS and struggling readers | [6 empty] | (O3b. Impliment with All IEPs with Dyslexia) | [8 empty] | Use as many pages as needed.
| Objective #4: |  | (Update 5.1.22) New Objective - Use Apps in ESY 7/1/22 (possibly obligate and expend 7/1/23)
II | Place symbol G (Goal) and Objectives (O1) above the month that the team projects actions to occur. | [17 empty] | Section II is a managerial time
Place an arrow or color bar along the funding source - projected costs/balances should be updated regularly. | [18 empty] | grid that follows the FY22 year.
| start |  |  |  | 2 |  | 3 | 1 & 2b | [6 empty] | Tip: Work backwards |  |  |  | Place in the Goal (G) and small
Source | 7.21 | 8.21 | 9.21 | 10.21 | 11.21 | 12.21 | 1.22 | 2.22 | 3.22 | 4.22 | 5.22 | 6.22 | Total |  | from end date to present. |  |  |  | steps (Objectives).
Local |  |  |  |  | pay for APP license 25k for all students with disabilities in LEA through 6/30/23 | [7 empty] | 13K |  | Tip: Have standing
State | RESC to Assess Needs 10k |  | 10k | [9 empty] | 10k |  | goal/source review |  |  |  | Determine funding source from
a. | [7 empty] | NEAT Training of Special Ed Staff 3k, |  |  |  |  | 3k |  | meetings with team |  |  |  | list codes below and place in
b. | [6 empty] | CEIS - stuggling readers nondisabled kids 1k | [5 empty] | 1k |  | on a regular basis. |  |  |  | arrows/color bar along
c. | [14 empty] | Tip: Consider running |  |  |  | the time line.
d. | [14 empty] | grant source scenarios
e. | [14 empty] | in LEA MOE Calculator |  |  |  | Place in projected running
f. | [14 empty] | throughout year. |  |  |  | balances in order to know status.
| 4 |  | 3a |  | 2b |  | 3a |  |  | G |  | End | obligate |  | liquidate |  | Grant Sources Codes/ Definitions List with
Source | 7.22 | 8.22 | 9.22 | 10.22 | 11.22 | 12.22 | 1.23 | 2.23 | 3.23 | 4.23 | 5.23 | 6.23 | 7.23 | 8.23 | 9.23 | Total | approximate cost funding/balance amount.
Local | NOTE: All School App is 50K only use 25K out of local Special Education budget. | [14 empty] | 12k | Local | Local Spec Ed Fund - 25k/150k
State | [16 empty] | State | ECS/ExcessCost Grant 10k/$ 100k
a. | IDEA Part B Salaries 17k | [14 empty] | 10k | a. | IDEA Part B 80k (611 - 20k/68K, 619 - 0k/12k)
b. | ESY IEPs 1k | [5 empty] | Manage IEPs 5k | [8 empty] | 6k | b. | ARP IDEA Part B $10K (611 - CEIS 1k/7k, 619 - 0k/2k)
c. |  |  | ESSER II Dyslexia 5k | [12 empty] | 5k | c. | Esser II - Dyslexia (5k/5k)
d. | ESSER II - Bonus 25k Dyslexia | [14 empty] | 25k | d. | Esser II - Bonus Dyslexia (25k/25k)
e. | [16 empty] | e.
f. | [16 empty] | f.

## Set B Ex, 1 Budget for Total
LEA Goals and Grant Source Management Timeline Worksheet
| LEA NAME: |  | Happy Town |  |  | Team Members: |  | TB, AB, AT, MT |  |  | Date: | 11.1.21 | Update: | 2.1.22, 5.1.22 |  |  |  | Guidance:
I | Write a goal that aligns with identified needs of the LEA and Students with Disabilities. Establish at least | [16 empty] | Section I is designed for the District
one Objective (others can be added later) to ensure the team is headed toward the attainable Goal. | [17 empty] | Team to develop sustainable supports
| Goal (G): |  | Establish the use of Read and Writing Apps across the District. | [14 empty] | through small steps (objectives) aligned
| Objective #1: |  | Contact NEAT/SERC schedule consult and training | [14 empty] | to LEA initiatives for accomplishable
| Objective #2: |  | Get License for Read and Write | [5 empty] | (O2b. Udate apps as pilot in spring/across school in fall) | [8 empty] | goals with braided grant sources.
| Objective #3: |  | Impliment CEIS and struggling readers | [6 empty] | (O3b. Impliment with All IEPs with Dyslexia) | [7 empty] | Use as many pages as needed.
| Objective #4: |  | (Update 5.1.22) New Objective - Use Apps in ESY 7/1/22 (possibly obligate and expend 7/1/23)
Section II is a managerial time
II | Place symbol G (Goal) and Objectives (O1) above the month that the team projects actions to occur. | [16 empty] | grid that follows the FY22 year.
Place an arrow or color bar along the funding source - projected costs/balances should be updated regularly.
Place in the Goal (G) and small
| start |  |  |  | 2 |  | 3 | 1 & 2b |  |  |  |  | FY22 |  | Tip: Work backwards |  |  | steps (Objectives).
Source | 7.21 | 8.21 | 9.21 | 10.21 | 11.21 | 12.21 | 1.22 | 2.22 | 3.22 | 4.22 | 5.22 | 6.22 | Subtotal |  | from end date..
Local |  |  |  |  | pay for APP license 25k for all students with disabilities in LEA through 6/30/23 | [7 empty] | 13K |  | Tip: Have standing |  |  | Determine funding source from
State | RESC to Assess Needs 10k | [11 empty] | 10 |  | goal/source review |  |  | list codes below and place in
a. | [7 empty] | NEAT Training of Special Ed Staff 3k, |  |  |  |  | 3k |  | meetings with team |  |  | arrows/color bar along
b. | [12 empty] | 0 |  | on a regular basis. |  |  | the time line and projected budget.
c. | [6 empty] | CEIS - stuggling readers nondisabled kids 1k | [5 empty] | 1k |  | Tip: Consider running
d. | [14 empty] | grant source scenarios |  |  | Place in projected running
e. | [14 empty] | in LEA MOE Calculator |  |  | balances in order to know status.
f. | [14 empty] | throughout year.
Grant Sources Codes/ Definitions List
| 4 |  | 3a |  | 2b |  | 3a |  |  | G |  | End | obligate |  | liquidate | FY22 | with approximate funding/balance amount.
Source | 7.22 | 8.22 | 9.22 | 10.22 | 11.22 | 12.22 | 1.23 | 2.23 | 3.23 | 4.23 | 5.23 | 6.23 | 7.23 | 8.23 | 9.23 | Subtotal |  |  | FY22 Total | Balance | Ependiture | Remain
Local | NOTE: All School App is 50K only use 25K out of local Special Education budget. | [14 empty] | 25k | Local Spec Ed Fund - 25k/150k |  |  | 150000 | 25000 | 125000
State | [15 empty] | 0 | State ECS/ExcessCost Grant 0k/$ 100k |  |  | 100000 | 10000 | 90000
a. | IDEA Part B Salaries 17k | [14 empty] | 20k | a. IDEA Part B 80k (611 - 20k/68K, 619 - 0k/12k) |  |  | 80000 | 20000 | 60000
b. | ESY IEPs 1k | [5 empty] | Manage IEPs 6k | [8 empty] | 7k | b. ARP IDEA Part B $10K (611 - CEIS 1k/7k, 619 - 0k/2k) |  |  | 10000 | 7000 | 3000
c. | [15 empty] | 1k | c. ARP IDEA Part B 611 - CEIS 1k/1k 619 0k/0k |  |  | 1000 | 1000 | 0
d. |  |  | ESSER II Dyslexia 5k | [12 empty] | 5k | d. Esser II - Dyslexia (5k/5k) |  |  | 5000 | 5000 | 0
d. | ESSER II - Bonus 25k Dyslexia | [15 empty] | d. | Esser II - Bonus Dyslexia (25k/25k) |  | 25000 | 25000 | 0
f. | [16 empty] | f.

## Set B Ex, 2 Budget for Activit
LEA Goals and Grant Source Management Timeline Worksheet
| LEA NAME: |  | Happy Town |  |  | Team Members: |  | TB, AB, AT, MT |  |  | Date: | 11.1.21 | Update: | 2.1.22, 5.1.22 |  |  |  | Guidance:
I | Write a goal that aligns with identified needs of the LEA and Students with Disabilities. Establish at least | [16 empty] | Section I is designed for the District
one Objective (others can be added later) to ensure the team is headed toward the attainable Goal. | [17 empty] | Team to develop sustainable supports
| Goal (G): |  | Establish the use of Read and Writing Apps across the District. | [14 empty] | through small steps (objectives) aligned
| Objective #1: |  | Contact NEAT/SERC schedule consult and training | [14 empty] | to LEA initiatives for accomplishable
| Objective #2: |  | Get License for Read and Write | [5 empty] | (O2b. Udate apps as pilot in spring/across school in fall) | [8 empty] | goals with braided grant sources.
| Objective #3: |  | Impliment CEIS and struggling readers | [6 empty] | (O3b. Impliment with All IEPs with Dyslexia) | [7 empty] | Use as many pages as needed.
| Objective #4: |  | (Update 5.1.22) New Objective - Use Apps in ESY 7/1/22 (possibly obligate and expend 7/1/23)
Section II is a managerial time
II | Place symbol G (Goal) and Objectives (O1) above the month that the team projects actions to occur. | [16 empty] | grid that follows the FY22 year.
Place an arrow or color bar along the funding source - projected costs/balances should be updated regularly.
Place in the Goal (G) and small
| start |  |  |  | 2 |  | 3 | 1 & 2b |  |  |  |  | FY22 |  | Tip: Work backwards |  |  | steps (Objectives).
Source | 7.21 | 8.21 | 9.21 | 10.21 | 11.21 | 12.21 | 1.22 | 2.22 | 3.22 | 4.22 | 5.22 | 6.22 | Subtotal |  | from end date..
Local |  |  |  |  | pay for APP license 25k for all students with disabilities in LEA through 6/30/23 | [7 empty] | 13K |  | Tip: Have standing |  |  | Determine funding source from
State | RESC to Assess Needs 10k | [11 empty] | 10 |  | goal/source review |  |  | list codes below and place in
a. | [7 empty] | NEAT Training of Special Ed Staff 3k, |  |  |  |  | 3k |  | meetings with team |  |  | arrows/color bar along
b. | [12 empty] | 0 |  | on a regular basis. |  |  | the time line and projected budget.
c. | [6 empty] | CEIS - stuggling readers nondisabled kids 1k | [5 empty] | 1k |  | Tip: Consider running
d. | [14 empty] | grant source scenarios |  |  | Place in projected running
e. | [14 empty] | in LEA MOE Calculator |  |  | balances in order to know status.
f. | [14 empty] | throughout year.
Grant Sources Codes/ Definitions List
| 4 |  | 3a |  | 2b |  | 3a |  |  | G |  | End | obligate |  | liquidate | FY22 | with approximate funding/balance amount.
Source | 7.22 | 8.22 | 9.22 | 10.22 | 11.22 | 12.22 | 1.23 | 2.23 | 3.23 | 4.23 | 5.23 | 6.23 | 7.23 | 8.23 | 9.23 | Subtotal |  |  | FY22 Total | Balance | Ependiture | Remain
Local | NOTE: All School App is 50K only use 25K out of local Special Education budget. | [14 empty] | 25k | Local Spec Ed Fund - 25k/150k |  |  | 30000 | 25000 | 5000
State | [15 empty] | 0 | State ECS/ExcessCost Grant 0k/$ 100k |  |  | 10000 | 10000 | 0
a. | IDEA Part B Salaries 17k | [14 empty] | 20k | a. IDEA Part B 80k (611 - 20k/68K, 619 - 0k/12k) |  |  | 20000 | 20000 | 0
b. | ESY IEPs 1k | [5 empty] | Dyslexia IEPs 6k | [8 empty] | 7k | b. ARP IDEA Part B $10K (611 - CEIS 1k/7k, 619 - 0k/2k) |  |  | 10000 | 12000 | -2000
c. | [15 empty] | 1k | c. ARP IDEA Part B 611 - CEIS 1k/1k 619 0k/0k |  |  | 1000 | 1000 | 0
d. |  |  | ESSER II Dyslexia 5k | [12 empty] | 5k | d. Esser II - Dyslexia (5k/5k) |  |  | 5000 | 5000 | 0
d. | ESSER II - Bonus 25k Dyslexia | [14 empty] | 25K | d. | Esser II - Bonus Dyslexia (25k/25k) |  | 25000 | 25000 | 0
f. | [16 empty] | f.